## All (hidden)
Discipline | Content | WVF | Work Steps
Civil
| Concrete Paving | 8.704% | Bed Preparation & Compaction | Wire Mesh (Kg) & Plastic Sheet | Form Work & Joints | Concrete work (M3) | Curing | Final Check
|  |  | 20% | 25% | 10% | 40% | 3% | 2%
| Cable Trench | 4.239% | Excavation (M3) | Preparation | Sand Bedding (M3) | Concrete Block Laying | Backfill & Compaction (M3) | Final Check
|  |  | 20% | 25% | 11% | 40% | 3% | 1%
| UG Trench | 7.997% | Excavation (M3) | Preparation | Sand Fill (M3) | Backfill & Compaction (M3) | Final Check
|  |  | 30% | 10% | 19% | 40% | 1%
| U Ditch (Open Ditch) | 5.18% | Excavation (M3) | Preparation & Lean Concrete (M3) | Rebar (Kg) | Form Work (Kg) | Main Concrete (M3) | Backfill & Compaction (M3) | Final Check
|  |  | 15% | 10% | 20% | 15% | 29% | 10% | 1%
| Culvert (Cubes beside road) | 0.3061% | Excavation | Preparation | Precast Cube | Transport & Placing | Finishing | Backfill | Final Check
|  |  | 10% | 5% | 44% | 15% | 15% | 10% | 1%
| Equipment, PL FDN | 37.1% | Excavation | Lean Conc. | Rebar | Formwork | Anchor Bolt Set. | Placing Concrete (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 10% | 5% | 22% | 15% | 5% | 29% | 3% | 2% | 8% | 1%
| Duct Bank | 1.199% | Excavation | Lean Concrete | Rebar | Formwork | Placing Concrete | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 10% | 5% | 20% | 25% | 26% | 3% | 2% | 8% | 1%
| Pit/Pond/Sump/Basin | 1.329% | Excavation | Lean Concrete | Rebar | Form Work | Main Concrete | Curing | Bitmin. Coat | Backfill & Compaction | Cheqered Plate Cap Installation | Final Check
|  |  | 5% | 2% | 20% | 22% | 29% | 3% | 5% | 8% | 5% | 1%
| Manhole, Catch Basin, Sump Valvebox | 1.651% | Excavation | Lean Concrete | Rebar | Form Work | Main Concrete | Curing | Bitumin. Coat | Backfill & Compaction | Cast Iron Cap Installation | Final Check
|  |  | 5% | 2% | 20% | 22% | 29% | 3% | 5% | 8% | 5% | 1%
| Pipe Sleeper | 6.26% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 10% | 5% | 20% | 15% | 34% | 2% | 5% | 8% | 1%
| Pipe Rack & Equipment Structure | 19.38% | Excavation | Lean Conc. | Rebar | Formwork & Embeded Plate | Anchor Bolt Set. | Placing Concrete . | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 10% | 3% | 22% | 20% | 5% | 26% | 3% | 2% | 8% | 1%
| Dikes/Bund Wall/Spillage Wall | 6.208% | Excavation | Disposal & Lean Concrete | Rebar | Formwork | Placing Concrete | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 5% | 5% | 22% | 25% | 26% | 3% | 5% | 8% | 1%
| Retaining Wall | 0.2235% | Excavation | Disposal & Lean Concrete | Rebar | Formwork | Placing Concrete | Curing | Bitumin. Coat | Backfill & Compaction | Final Check
|  |  | 5% | 5% | 20% | 25% | 26% | 3% | 7% | 8% | 1%
| UG RC | 0.2235% | Construction | Pipe Laying/Fit-up | Final Inspection
|  |  | 40% | 45% | 15%
Welding and NDT Procedures qualification
| Prepare and qualify welding procedures for structural and pipe welding | 0.5% | As per Issue Doc.
| Qualification of welders including lab testing for structural and piping | 0.5% | As per piping & St. Str progress
| Qualification of welding equipment | 0.5% | As per piping progress
| Maintaining welder qualification records | 0.5% | As per piping progress
| Monitoring welder performance | 0.5% | As per piping progress
| Prepare and NDT Procedures and obtain certification | 30% | As per Issue Doc.
| Qualification of NDT equipment and dimensional control (UT, RT, MT) | 0.5% | As per NDT equipment Set
| Qualification of equipment operators for NDT and dimensional control | 0.5% | As per NDT Teams
| Perform NDT as per the procedures | 8% | As per piping progress
| Supply of associated Elec. Power, consumables, Materials construction equipments | 8% | As per piping progress
| Prepare PWHT procedure and obtain certification | 30% | As per Issue Doc.
| Perform PWHT testing | 8% | As per piping progress
| Provide and maintain secure storage for radioactive sources | 12% | Provided (Will be completed, As first part of piping starts)
| Implement specific safety procedures relating to radioactive sources | 0.5% | As per Issue Doc.
Steel Work
| Equipment Structure Erecion | 48.98% | MATERIAL DELIVERY AT JOB SITE | ERECTION | ALIGNMENT | BOLT TIGHTENING & TEST | GROUTING | PUNCH CLEAR
|  |  | 15% | 69% | 5% | 5% | 5% | 1%
| Pipe Rack Erection | 45.04% | 15% | 69% | 5% | 5% | 5% | 1%
|  |  | MATERIAL DELIVERY AT JOB SITE | ERECTION | ALIGNMENT | BOLT TIGHTENING & TEST | GROUTING | PUNCH CLEAR
| Platform & Ladder | 4.977% | MATERIAL DELIVERY AT JOB SITE | ERECTION | ALIGNMENT | BOLT TIGHTENING & TEST | PUNCH CLEAR
|  |  | 15% | 69% | 5% | 6% | 5%
| Shelter | 1% | Excavation | Lean Concrete | Rebar | Main Concrete | Ground Beam & core | Floor Slab | Steel Structure | Cladding | Lighting | Apron & Drain
|  |  | 4% | 2% | 4% | 5% | 5% | 5% | 59% | 10% | 5% | 1%
Piping
| Piping Support Shop Fabrication | 5% | Cutting | Assembling | Welding | NDT | Final Inspection
|  |  | 20% | 30% | 40% | 5% | 5%
| Piping Support Field Installation | 5% | Assembly in Position | Welding/Bolting | Dimension Check | NDT | Final Inspection (Ready for Hydro-Test)
|  |  | 50% | 35% | 5% | 5% | 5%
| Piping Shop Fabrication | 34% | Handeling (From Storege) | Beveling | Fit Up | Welding | NDT/PWHT | Handling to Sand Blost Shop
|  |  | 10% | 13% | 34% | 41% | 2%
| Piping Field Erection | 41% | Handeling From Sand Blost Shop | Erection | Fit Up | Welding | NDT/PWHT | Identification Mark | Final Inspection (Ready for Hydro-Test)
|  |  | 10% | 10% | 20% | 40% | 10% | 2% | 8%
| Valve Erection | 4% | Handeling | Install | Fix Bolting | Final Inspection (Ready for Hydro-Test)
|  |  | 15% | 50% | 20% | 15%
| Steam Tracing | 3% | Erection | Assembly | Welding/Threading | Final Inspection
|  |  | 15% | 35% | 45% | 5%
| U/G Piping | 8% | Shop fabrication | Laying/Assembling | Welding/Bonding | Hydro-Test | Coating/Wrapping | Final Inspection
|  |  | 30% | 27% | 28% | 5% | 5% | 5%
Painting
| Structure |  | Sandblost & Primer | Intermediate Coat. | Finish Coating | Punch Clear | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
| Piping |  | Sandblost& Primer | Intermediate Coat. | Finish Coating | Tuch-Up,Punch Clear & Finish | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
| Equipment |  | Sandblost& Primer | Intermediate Coat. | Finish Coating | Tuch-Up,Punch Clear & Finish | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
| Fire proofing Structure |  | Preparation & Wire Mesh | Gunite | Cleaning | Final Inspection
|  |  | 40% | 50% | 5% | 5%
| Fire proofing Equipment |  | Preparation & Wire Mesh | Gunite | Cleaning | Final Inspection
|  |  | 40% | 50% | 5% | 5%
Insulation
| Piping Cold |  | Material Preparation at Job site | Insulation | METAL Jacketing | Sealing Work | Cleaning & Punch Clear | Final Inspection
|  |  | 10% | 55% | 20% | 5% | 5% | 5%
| Piping Hot |  | Material Preparation at Job site | Insulation | METAL Jacketing | Sealing Work | Cleaning & Punch Clear | Final Inspection
|  |  | 10% | 55% | 20% | 5% | 5% | 5%
| Equipment Cold |  | Material Preparation at Job site | Insulation | METAL Jacketing | Sealing Work | Cleaning & Punch Clear | Final Inspection
|  |  | 10% | 55% | 20% | 5% | 5% | 5%
| Equipment Hot |  | Material Preparation at Job site | Insulation | METAL Jacketing | Sealing Work | Cleaning & Punch Clear | Final Inspection
|  |  | 10% | 55% | 20% | 5% | 5% | 5%
HVAC
| Equipment Installation | 28.88% | Handling | INSTALLATION | ALIGNMENT | FINAL INSPECTION
|  |  | 5% | 70% | 20% | 5%
| Ducting Work | 27.98% | Handling | Duct Fabrication | Duct Insulation | Duct Installation | Blast Proof Valve | Air Terminal | Sand Trap Louver/Sound Attenuator | All Kind of Galv. Damper | Flexible Canvas Connection | Duct Lining | Lighting Test / FINAL INSPECTION
|  |  | 5% | 30% | 21% | 20% | 2% | 1% | 1% | 4% | 1% | 10% | 5%
| Piping | 27.35% | Handling | Fit-Up | Installation | Valve Installation |  | Welding | Insulation | Hydro Test | Clading | FINAL INSPECTION
|  |  | 5% | 30% | 15% | 4% |  | 25% | 12% | 2% | 2% | 5%
| Electrical Work | 6.53% | Handling | Conduit Installation | Ladder Installation | Cabling | Termination | FINAL INSPECTION
|  |  | 5% | 18% | 40% | 30% | 2% | 5%
| Control Work | 3.61% | Handling | Conduit Installation | Tray Installation | Cabling | Termination | Control Device Installation | FINAL INSPECTION
|  |  | 5% | 15% | 15% | 40% | 10% | 10% | 5%
| Plumbing Works | 2.47% | Handling | Waste, Drain & Vent Piping and Test | Domestic Water Piping and Test | Plumbing Fixture Installation | FINAL INSPECTION
|  |  | 5% | 35% | 50% | 7% | 3%
| Fire Fighting | 3.18% | Handing | Piping | Fire Extinguishers installation | Hydro Test | FINAL INSPECTION
|  |  | 5% | 45% | 44% | 3% | 3%
| Plumbing Works | ? | Handling | Waste, Drain & Vent Piping and Test | Domestic Water Piping and Test | Plumbing Fixture Installation | FINAL INSPECTION
|  |  | 5% | 35% | 50% | 7% | 3%
Electrical
| Lighting work | 4.688% | Handling | LIGHTING POLE/Support INSTALLATION | LIGHTING FIXTURE INSTALLATION | TRAY INSTALLATION | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | TEST | FINAL INSPECTION
|  |  | 5% | 5% | 10% | 25% | 40% | 5% | 5% | 3% | 2%
| Main Lighting Work | 2.696% | Handling | LIGHTING POLE/Support INSTALLATION | LIGHTING FIXTURE INSTALLATION | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | Fuse Box Installation | TEST | FINAL INSPECTION
|  |  | 5% | 10% | 15% | 40% | 5% | 5% | 15% | 3% | 2%
| Grounding work | 9.598% | Handling | EARTH PIT/EARTH RODE INSTALLATION | WIRE LAYING | COMPRESSION CLAMP/CADWELD CONNECTION | EARTHING DISPATCHER/EARTHING LUG | TEST | FINAL INSPECTION
|  |  | 5% | 15% | 45% | 20% | 10% | 3% | 2%
| Cathodic protection | 2.855% | Handling | ANODE INSTALLATION | CABLE LAYING | BOX INSTALLATION (HALFCELL,TEST, POSITIVE & NEGATIVE) | EQUIPMENT INSTALLATION (TR, Resistance Band Box) | TERMINATION INCLUDING CAD WELD | Ref. Electrod Installation | SANDFILL | FINAL INSPECTION
|  |  | 5% | 5% | 30% | 20% | 15% | 10% | 10% | 3% | 2%
| Cable tray Install | 13.32% | Handling | SUPPORT FABRICATION | SUPPORT INSTALLATION | TRAY / LADDER INSTALLATION | FINAL INSPECTION
|  |  | 5% | 35% | 20% | 38% | 2%
| Conduit Install | 9.781% | Handling | SUPPORT FABRICATION | SUPPORT INSTALLATION | CONDUIT INSTALLATION | FINAL INSPECTION
|  |  | 5% | 30% | 15% | 45% | 5%
| Equipment install | 16.07% | Handling | INSTALLATION | TERMINATION | TEST & FINAL CHECK
|  |  | 5% | 80% | 10% | 5%
| Cabling & Termination | 37.21% | Handling | CABLE PULLING | GLAND | TERMINATION | MEGGER TEST | FINAL CHECK
|  |  | 5% | 80% | 5% | 5% | 3% | 2%
| Fire Alarm system | 3.779% | Handling | EQUIPMENT INSTALLATION | CONDUIT INSTALLATION | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | TEST | FINAL INSPECTION
|  |  | 5% | 20% | 15% | 40% | 5% | 5% | 5% | 5%
Building and Artichectural
Substation | CONCRETE STRUCTURE | 65% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Check
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
View Gallery | CONCRETE STRUCTURE | 30% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
|  | 35% | Prefabrication | Installation | Alignment | Bolting | Final Check
|  |  | 60% | 15% | 10% | 10% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Fire Fighting | Final Inspection
|  |  | 5% | 28.17% | 52.36% | 7.715% | 5.024% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Check
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 20%
|  |  |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Gate House | CONCRETE STRUCTURE | 60% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Final Inspection
|  |  | 5% | 28.17% | 60.81% | 4.291% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Check
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Fire Fighting Building | CONCRETE STRUCTURE | 60% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 26.17% | 35.81% | 21.05% | 6.215% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Check
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Site Toilets 8 Nos | CONCRETE STRUCTURE | 60% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Final Inspection
|  |  | 5% | 2.433% | 80.81% | 10.02% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Support | Final Check
|  |  | 13% | 13% | 38.22% | 21% | 8% | 5% | 1.78%
| Architectural | 25% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Administration Building | CONCRETE STRUCTURE | 60% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Canteen | CONCRETE STRUCTURE | 60% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Control Room | CONCRETE STRUCTURE |  | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) |  | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK |  | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Contractor Building | CONCRETE STRUCTURE |  | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) |  | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK |  | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Laboratory | CONCRETE STRUCTURE |  | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) |  | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK |  | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Security Building | CONCRETE STRUCTURE |  | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) |  | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK |  | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Telecom Building | CONCRETE STRUCTURE |  | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) |  | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK |  | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural |  | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Buildings With Steel Structure: Out Door & In Door Ware House & Mainworkshop & Vehicle Maintenance | CONCRETE STRUCTURE | 30% | Exca. & Lean Conc. | Disposal | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| STEEL STRUCTURE | 35% | Prefabrication | Installation | Alignment | Bolting
|  |  | 60% | 20% | 10% | 10%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tey & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanazed | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panles Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Arch. | 20% | External Works | External Works | External Works | Interior Works | Interior Works | Interior Works
|  |  | Side Walk | Wall | Roof | Floor | Wall | Roof
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Equipment Packages
| Drum/Vessel |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Boiler |  | Material collection | Chipping & Padding | Installation | Align | Steel work, Coil Connection | Accessory Install | Final Inspection
|  |  | 10% | 5% | 43% | 10% | 15% | 15% | 2%
| Column |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Reactor |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Heat Exchanger |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Filter |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Furnace Blower/ Heater |  | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 75% | 10% | 2.5% | 10% | 2.5%
| Ejector |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 10% | 60% | 8% | 2% | 8% | 2%
| Gas Compressor/Turbine |  | Material collection | Chipping & Padding | Turbine/Generator Install | 1st Alignment | Steel Structure | Duct/Accessory | 2nd Align/Grouting/Coupling | Grouting | Final Inspection
|  |  | 10% | 5% | 43% | 15% | 10% | 5% | 5% | 5% | 2%
| Compressor |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | Final Alignment / Piping | Final Inspection
|  |  | 10% | 10% | 48% | 15% | 5% | 10% | 2%
| Mixer Agitator |  | Material collection | Chipping & Padding | ERECTION | Alignment / Leveling | Grouting | Final Alignment w/ Piping | Final Inspection
|  |  | 10% | 10% | 60% | 5% | 5% | 8% | 2%
| Pump |  | Material collection | Chipping & Padding | ERECTION | 1st Alignment | Grouting | 2nd Alignment | Final Inspection
|  |  | 10% | 10% | 48% | 15% | 5% | 10% | 2%
| Package Equipment |  | Material collection | Chipping & Padding | Assembling/Install | Skid Align | Accessory Install | 2nd Align | Final Inspection
|  |  | 10% | 10% | 58% | 10% | 5% | 5% | 2%
| Overhead Crane |  | Material collection | Erect Rail Frame | Main Frame Install | Crane Install | Align | Final Inspection
|  |  | 5% | 30% | 35% | 20% | 8% | 2%
| Internals/Tray |  | Material collection | Install | Inspection
|  |  | 10% | 88% | 2%
| Air Cooler |  | Material collection | Structure Ground Assembly | Structure Erection | Tube Bandle Erection | Ground Assemby of Plenum | Plenum Chamber Installation | Motor Installation | Blade Installation | Pulley Installation | Ladder & Platform | Pully Adjustment | Shaft Alignment | Blade Angle & Tip Clearance | Tube Connection | Final Inspection
|  |  | 5% | 15% | 6% | 17% | 8% | 10% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 2% | 2%
| FF Tank |  | Foundation Preparation | Erection & Welding of Bottom Plate | Erection & Welding of Annular Plate | Erection & Welding of Shell Plate | Erection & Welding of Roof Plate (Including Roof Support) | Erection & Welding of Accessory | Hydro Test | Drainage & Cleaning out (Final Inspection)
|  |  | 5% | 10% | 5% | 50% | 15% | 10% | 0% | 5%
| Condensate Tank |  | Foundation Preparation | Electrical Work (Cathodic Protection) | Erection & Welding of Bottom Plate | Erection & Welding of Annular Plate | Erection & Welding of Shell Plate | Erection & Welding of Roof Plate (Including Roof Support) | Erection & Welding of Accessory | Hydro Test | Drainage & Cleaning out (Final Inspection)
|  |  | 15% | 2% | 5% | 3% | 50% | 15% | 5% | 0% | 5%
| LPG Tank |  | Foundation Preparation | Bottom Work | Concrete Wall | Wall Plate | Roof Assembly / Installation | Roof Concrete | Accessory Installation | Mechanical Work | Insulation | Test
|  |  | 2% | 5% | 60% | 10% | 3% | 2% | 2% | 10% | 4% | 2%
| Flare |  | Material collection | Tip Assembling/Install | Align | Platform/Stair | Final Inspection
|  |  | 10% | 65% | 13% | 10% | 2%

## Welding
Job Phases And Work Steps (Onshore Facilities)
Welding and NDT Procedures qualification
row | JOB PHASES | W.F | WORK STEPS
1 | Prepare and qualify welding procedures (welding procedures qualification tests (WPQT) including lab,tests) for structural and pipe welding | 0.5% | As per Issue Doc.
2 | Qualification of welders including lab testing for structural and pipe welding | 0.5% | As per piping & St. Str progress
3 | Qualification of welding equipment | 0.5% | As per piping progress
4 | Maintaining welder qualification records | 0.5% | As per piping progress
5 | Monitoring welder performance | 0.5% | As per piping progress
6 | Prepare and NDT Procedures and obtain certification | 38% | As per Issue Doc.
7 | Qualification of NDT equipment and dimensional control (UT, RT, MT) | 0.5% | As per NDT progress
8 | Qualification of equipment operators for NDT and dimensional control | 0.5% | As per NDT progress
9 | Supply of associated Elec. Power, consumables, Materials construction equipments | 8% | As per piping progress
10 | Prepare PWHT procedure and obtain certification | 38% | As per Issue Doc.
11 | Provide and maintain secure storage for radioactive sources | 12% | As perform
12 | Implement specific safety procedures relating to radioactive sources | 0.5% | As per Issue Doc.
Total |  | 100%

## Civil
Job Phases And Work Steps (Onshore Facilities) Civil Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8 | WORK STEP9 | WORK STEP10
1 | Concrete Paving | 8.7% | Bed Preparation & Compaction | Wire Mesh/Rebar (Kg) & Plastic Sheet | Form Work & Joints | Concrete Pouring (M3) | Curing | Final Inspection
|  |  | 20% | 25% | 10% | 40% | 3% | 2%
2 | Gravell Paving |  | Bed Preparation & Compaction | Gravelling | Final Inspection
|  |  | 20% | 78% | 2%
3 | Cable Trench |  | Excavation | Lean Concrete, Rebar, … | Sand Bedding (M3) | Concrete Block Laying | Backfill & Compaction (M3) | Final Inspection
|  |  | 20% | 25% | 11% | 40% | 3% | 1%
4 | UG Trench |  | Excavation | Preparation | Sand Fill (M3) | Backfill & Compaction (M3) | Final Inspection
|  |  | 30% | 10% | 19% | 40% | 1%
5 | U Ditch (Open Ditch) |  | Excavation | Preparation & Lean Concrete (M3) | Rebar | Form Work | Concrete Pouring (M3) | Backfill & Compaction (M3) | Final Inspection
|  |  | 15% | 10% | 20% | 15% | 29% | 10% | 1%
6 | Culvert (Cubes beside road) |  | Excavation | Preparation & Lean Concrete (M3) | Rebar | Form Work | Concrete Pouring (M3) | Backfill & Compaction (M3) | Final Inspection
|  |  | 15% | 10% | 20% | 15% | 29% | 10% | 1%
7 | Equipment, PL FDN |  | Excavation | Lean Concrete | Rebar | Formwork | Anchor Bolt Set. | Concrete Pouring (M3) | Curing | Bitumen. Coat | Backfill & Compaction | Final Inspection
|  |  | 10% | 5% | 25% | 15% | 5% | 30% | 2% | 2% | 5% | 1%
8 | Duct Bank |  | Excavation | Lean Concrete | Rebar | PVC | Formwork | Concrete Pouring (M3) | Curing | Bitumen. Coat | Backfill & Compaction | Final Inspection
|  |  | 10% | 5% | 20% | 10% | 20% | 25% | 2% | 2% | 5% | 1%
9 | Pit/Pond/Sump/Basin |  | Excavation | Lean Concrete | Rebar | Form Work | Concrete Pouring (M3) | Curing | Bitumen. Coat | Backfill & Compaction | Cheqered Plate Cap Installation | Final Inspection
|  |  | 5% | 2% | 21% | 22% | 32% | 2% | 5% | 5% | 5% | 1%
10 | Manhole, Catch Basin, Sump Valvebox |  | Excavation | Lean Concrete | Rebar | Form Work | Concrete Pouring (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Cast Iron Cap Installation | Final Inspection
|  |  | 5% | 2% | 21% | 22% | 32% | 2% | 5% | 5% | 5% | 1%
11 | Pipe Sleeper |  | Excavation | Lean Concrete | Rebar | Formwork | Concrete Pouring (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Final Inspection
|  |  | 10% | 5% | 21% | 15% | 36% | 2% | 5% | 5% | 1%
12 | Pipe Rack & Equipment Structure & Shelter |  | Excavation | Lean Concrete | Rebar | Formwork & Embeded Plate | Anchor Bolt Set. | Concrete Pouring (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Final Inspection
|  |  | 10% | 3% | 23% | 20% | 5% | 29% | 2% | 2% | 5% | 1%
13 | Dikes/Bund Wall/Spillage Wall |  | Excavation | Lean Concrete | Rebar | Formwork | Concrete Pouring (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Final Inspection
|  |  | 5% | 5% | 23% | 25% | 29% | 2% | 5% | 5% | 1%
14 | Retaining Wall |  | Excavation | Lean Concrete | Rebar | Formwork | Concrete Pouring (M3) | Curing | Bitumin. Coat | Backfill & Compaction | Final Inspection
|  |  | 10% | 5% | 21% | 25% | 26% | 2% | 5% | 5% | 1%
15 | UG RC |  | Excavation | Preparation | Pipe laying | Fit up
|  |  | 20% | 20% | 45% | 15%
16 | Road |  | Sub-Grade | Sub-Base | Base | Binder Course | Surface Course
|  |  | 15% | 20% | 20% | 20% | 25%

## Piping
Job Phases And Work Steps (Onshore Facilities) Piping Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6
1 | Piping Support Shop Fabrication -(AG) | 5% | Cutting | Assembling | Welding | NDT
|  |  | 20% | 30% | 45% | 5%
2 | Piping Support Field Installation -(AG) |  | Assembly in Position | Welding/Bolting | Dimension Check | NDT | Final Inspection (Ready for Hydro-Test)
|  |  | 50% | 35% | 5% | 5% | 5%
3 | Piping Shop Fabrication - (AG) |  | Handling (From Storage) | Beveling | Fit Up | Welding | NDT/PWHT
|  |  | 5% | 15% | 33% | 42% | 5%
4 | Piping Field Erection - (AG) |  | Handling From Sand Blost Shop | Erection | Fit Up | Welding | NDT/PWHT | Final Inspection (Ready for Hydro-Test)
|  |  | 5% | 20% | 20% | 41% | 10% | 4%
5 | Valve Erection - (AG) |  | Coincide with LINE CHECK progress
6 | Steam Tracing - (AG) |  | Erection | Assembly | Welding/Threading | Final Inspection
|  |  | 15% | 40% | 40% | 5%
7 | U/G Piping (Metal) |  | Laying | Fit Up | Welding | Hydro-Test | Coating/Wrapping | Final Inspection
|  |  | 25% | 28% | 35% | 4% | 3% | 5%
8 | U/G Piping (Non Metal) |  | Laying | Bonding | Hydro-Test | Final Inspection
|  |  | 30% | 60% | 5% | 5%

## Electrical
Job Phases And Work Steps (Onshore Facilities) Electrical Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8 | WORK STEP9
1 | Lighting work |  | Handling | LIGHTING POLE/Support INSTALLATION | LIGHTING FIXTURE INSTALLATION | TRAY and CONDUIT INSTALLATION | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | TEST | FINAL INSPECTION
|  |  | 5% | 5% | 10% | 20% | 40% | 5% | 5% | 5% | 5%
2 | Main Lighting Work (Street lighting work) |  | Handling | LIGHTING POLE/Support and Fuse Box Installation | LIGHTING FIXTURE INSTALLATION | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | TEST | FINAL INSPECTION
|  |  | 6% | 15% | 20% | 40% | 5% | 5% | 4% | 5%
3 | Grounding work |  | Handling | EARTH PIT/EARTH RODE INSTALLATION | WIRE LAYING | COMPRESSION CLAMP/CADWELD CONNECTION | EARTHING DISPATCHER/EARTHING LUG | TEST | FINAL INSPECTION
|  |  | 5% | 15% | 40% | 20% | 10% | 5% | 5%
4 | Cathodic protection For Drums and Tanks * |  | Handling | ANODE INSTALLATION | Reference Electrod Installation | CABLE LAYING | BOX INSTALLATION (HALFCELL,TEST, POSITIVE & NEGATIVE) | EQUIPMENT INSTALLATION (Trans, Resistance Band Box) | TERMINATION INCLUDING CAD WELD | TEST | FINAL INSPECTION
|  |  | 5% | 23% | 5% | 34% | 5% | 15% | 5% | 5% | 3%
5 | Piping U/G Cathodic protection * |  | Handling | ANODE INSTALLATION | Reference Electrod Installation | CABLE LAYING | BOX INSTALLATION (HALFCELL,TEST, POSITIVE & NEGATIVE) | EQUIPMENT INSTALLATION (Trans, Resistance Band Box) | TERMINATION INCLUDING CAD WELD | TEST and FINAL INSPECTION
|  |  | 5% | 8% | 27% | 20% | 15% | 10% | 10% | 5%
6 | Cable tray and Ladder Installaion |  | Handling | SUPPORT FABRICATION | SUPPORT INSTALLATION | TRAY / LADDER INSTALLATION | FINAL INSPECTION
|  |  | 5% | 35% | 20% | 35% | 5%
7 | Conduit Installation |  | Handling | SUPPORT FABRICATION | SUPPORT INSTALLATION | CONDUIT INSTALLATION | FINAL INSPECTION
|  |  | 5% | 30% | 15% | 45% | 5%
8 | Equipment installation |  | Handling | INSTALLATION | TERMINATION | TEST & FINAL INSPECTION
|  |  | 7% | 80% | 10% | 3%
9 | Cabling & Termination |  | Handling | CABLE PULLING | GLAND | TERMINATION and JOINT | Megger/ HV TEST | FINAL INSPECTION
|  |  | 5% | 70% | 5% | 10% | 8% | 2%

## Instrumentation
Job Phases And Work Steps (Onshore Facilities) Instrumentation Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8
1 | Cable tray and Ladder Installaion |  | Handling | SUPPORT FABRICATION | SUPPORT INSTALLATION | TRAY / LADDER INSTALLATION | FINAL INSPECTION
|  |  | 5% | 35% | 20% | 35% | 5%
2 | Junction Box |  | Handling | SUPPORT FABRICATION and Installation | Setting/Installation | Final Inspection
|  |  | 5% | 20% | 70% | 5%
3 | Instrument Cabling |  | Handling | CABLE PULLING | GLAND | TERMINATION | calbe test | Final Inspection
|  |  | 10% | 65% | 5% | 10% | 5% | 5%
4 | Instrumentation (Devices Install) |  | Handling | Calibration | Support and Stand | Installation | Sunshade installation | Final Inspection
|  |  | 5% | 50% | 12% | 25% | 3% | 5%
5 | Piping & Tubing |  | Handling | Support Installation | Piping/Tubing | valve & accessories installation | Leak Test | Final Inspection
|  |  | 5% | 15% | 40% | 20% | 15% | 5%
6 | Equipment Install(Local panel/D.B Panel) |  | Handling | Support Fabrication | Support Installation | Panel Installation | FINAL INSPECTION
|  |  | 10% | 20% | 17% | 50% | 3%
7 | Fire Alarm system (added) |  | Handling | EQUIPMENT Installation | Support Installation | CONDUIT and TRAY Installation | CABLE LAYING | CABLE GLAND | CABLE TERMINATION | FINAL INSPECTION
|  |  | 5% | 20% | 5% | 15% | 40% | 5% | 5% | 5%

## Telecommunication
Job Phases And Work Steps (Onshore Facilities) Telecommunication Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5
1 | Telecommunication Cable Tray and Ladder |  | Handling | Support Fabrication | Support Installation | Installation Ladder/Tray | Final Inspection
|  |  | 4% | 40% | 20% | 31% | 5%
2 | Indoor Equipment |  | Handling | Support Fabrication | Support Installation | Equipment Installation | Final Inspection
|  |  | 4% | 6% | 10% | 75% | 5%
3 | Outdoor Equipment |  | Handling | Support Fabrication | Support Installation | Equipment Installation | Final Inspection
|  |  | 4% | 6% | 10% | 75% | 5%
4 | Boxes/Sockets/telephones (Indoor) |  | Handling | Support Fabrication | Support Installation | Equipment Installation | Final Inspection
|  |  | 4% | 6% | 10% | 75% | 5%
5 | Telecommunication Cabling/Glanding/Termination |  | Handling | Cable Laying | Gland/Termination | Final Inspection
|  |  | 10% | 70% | 15% | 5%
6 | Telecommunication Tower |  | Handling | Assembling and Installation | Final Inspection
|  |  | 35% | 60% | 5%

## HVAC
Job Phases And Work Steps (Onshore Facilities) HVAC Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8 | WORK STEP9 | WORK STEP10 | WORK STEP11 | WORK STEP12
1 | Equipment Installation |  | Handling | INSTALLATION | Alignment | FINAL INSPECTION
|  |  | 10% | 72% | 13% | 5%
2 | Ducting Work and Accessories |  | Handling | Duct Fabrication | Duct Installation | Lighting Test | Duct Insulation | Blast Proof Valve | Air Terminal | Sand Trap Louver/Sound Attenuator | All Kind of Galv. Damper | Flexible Canvas Connection | Duct Lining | FINAL INSPECTION
|  |  | 5% | 32% | 20% |  | 21% | 2% | 1% | 1% | 4% | 1% | 10% | 3%
3 | Piping Work |  | Handling | Fit-Up | Support Installation | Spool Erection | Welding | Hydro Test | Valve Installation | Insulation | Cladding | FINAL INSPECTION
|  |  | 5% | 32% | 15% |  | 25% | 2% | 4% | 12% | 2% | 3%
4 | Electrical Work |  | Handling | Conduit Installation | Ladder Installation | Cabling | Termination | FINAL INSPECTION
|  |  | 5% | 20% | 40% | 30% | 2% | 3%
5 | Control Work |  | Handling | Conduit Installation | Tray Installation | Cabling | Termination | Control Device Installation | FINAL INSPECTION
|  |  | 5% | 17% | 15% | 40% | 10% | 10% | 3%
6 | Plumbing Works |  | Handling | Waste, Drain & Vent Piping and Test | Domestic Water Piping and Test | Plumbing Fixture Installation | FINAL INSPECTION
|  |  | 5% | 37% | 48% | 7% | 3%
7 | Fire Fighting |  | Handing | Piping | Fire Extinguishers installation | Hydro Test | FINAL INSPECTION
|  |  | 5% | 47% | 42% | 3% | 3%

## Safety & Fire Fighting
Job Phases And Work Steps (Onshore Facilities) Safety & Fire Fighting Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4
1 | Local Equipment | 65% | Support Fabrication & Installation | Erection | FINAL INSPECTION
|  |  | 14% | 85% | 1%
2 | Deluge Valve | 35% | Handing | Installation | FINAL INSPECTION
|  |  | 5% | 94% | 1%

## Painting
Job Phases And Work Steps (Onshore Facilities) Painting Discipline
row | Job phase | W.F | Work Step1 | Work Step2 | Work Step3 | Work Step4 | Work Step5
1 | Structure |  | Sandblost & Primer | Intermediate Coat. | Finish Coating | Punch Clear | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
2 | Piping |  | Sandblost& Primer | Intermediate Coat. | Finish Coating | Tuch-Up,Punch Clear & Finish | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
3 | Equipment |  | Sandblost& Primer | Intermediate Coat. | Finish Coating | Tuch-Up,Punch Clear & Finish | Final Inspection
|  |  | 40% | 25% | 20% | 10% | 5%
4 | Fire proofing Structure |  | Preparation & Wire Mesh | Gunite | Cleaning | Final Inspection
|  |  | 40% | 50% | 5% | 5%
5 | Fire proofing Equipment |  | Preparation & Wire Mesh | Gunite | Cleaning | Final Inspection
|  |  | 40% | 50% | 5% | 5%

## Insulation
Job Phases And Work Steps (Onshore Facilities) Insulation Discipline
row | JOB PHASES | WVF | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5
1 | Piping Cold |  | Material Preparation and surface Preparation* | Insulation | METAL Jacketing and Sealing Work | Cleaning & Punch Clear | FINAL INSPECTION
|  |  | 10% | 55% | 27% | 3% | 5%
2 | Piping Hot |  | Material Preparation and surface Preparation* | Insulation | METAL Jacketing and Sealing Work | Cleaning & Punch Clear | FINAL INSPECTION
|  |  | 10% | 55% | 27% | 3% | 5%
3 | Equipment Cold |  | Material Preparation and surface Preparation* | Insulation | METAL Jacketing and Sealing Work | Cleaning & Punch Clear | FINAL INSPECTION
|  |  | 10% | 55% | 27% | 3% | 5%
4 | Equipment Hot |  | Material Preparation and surface Preparation* | Insulation | METAL Jacketing and Sealing Work | Cleaning & Punch Clear | FINAL INSPECTION
|  |  | 10% | 55% | 27% | 3% | 5%

## Building and Artichectural
Job Phases And Work Steps (Onshore Facilities) Building and Architectural Discipline
Buildings | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8 | WORK STEP9 | WORK STEP10 | WORK STEP11 | WORK STEP12 | WORK STEP13
Substation | CONCRETE STRUCTURE | 65% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Inspection
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
View Gallery | Civil Works | 30% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| STEEL STRUCTURE | 35% | Prefabrication | Installation | Alignment | Bolting | Final Inspection
|  |  | 60% | 15% | 10% | 10% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Fire Fighting | Final Inspection
|  |  | 5% | 28.17% | 52.36% | 7.715% | 5.024% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Inspection
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 20% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Gate House | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Final Inspection
|  |  | 5% | 28.17% | 60.81% | 4.291% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Inspection
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Fire Fighting Building | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 26.17% | 35.81% | 21.05% | 6.215% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Earthing | Telecomminucation & Paging System | Support | Final Inspection
|  |  | 13% | 10% | 31.22% | 21% | 8% | 3% | 7% | 5% | 1.78%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Site Toilets | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | Plumbing Works | Final Inspection
|  |  | 5% | 20% | 60% | 10.02% | 5%
| ELECTRICAL WORK | 10% | Tray Installation | Conduit Installation | Cabling and Wiring | Ltg Fixture, Detector, etc Install | Distribution Panel | Support | Final Inspection
|  |  | 13% | 13% | 38.22% | 21% | 8% | 5% | 1.78%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Administration Building | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Canteen | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Control Room | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Contractor Building | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Laboratory | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 28.81% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 1.73%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Security Building | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 29% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 2%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Telecom Building | CONCRETE STRUCTURE | 60% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 29% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 2%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 25% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%
Buildings With Steel Structure: Out Door & In Door Ware House & Main workshop & Vehicle Maintenance | CONCRETE STRUCTURE | 30% | Excavation | Lean Conc. | Rebar | Formwork | Placing Concrete | Curing | Backfill & Compaction
|  |  | 5% | 3% | 28% | 26% | 30% | 3% | 5%
| STEEL STRUCTURE | 35% | Prefabrication | Installation | Alignment | Bolting
|  |  | 60% | 20% | 10% | 10%
| MECHANICAL WORK (EXCL. HVAC) | 5% | Handling | HVAC Equipment | HVAC Ducting Work | HVAC Piping Work | HVAC Electrical Work | HVAC Control Work | Fire Fighting | Plumbing Works | Final Inspection
|  |  | 5% | 8.166% | 29% | 29.05% | 9.5% | 8% | 5.715% | 4.024% | 2%
| ELECTRICAL WORK | 10% | Conduit Work | Cable tray & cable ladder & Accessories Installation | Wire & Cable Pulling | Switch Installation | Power Outlet Installation | Lighting Installation | Cad Weld Connection | Support Material Galvanized | Fire & Gas System | Lightning Installation | Termination | Telecom & Paging Equipment | Distribution Panels Installation
|  |  | 23% | 15.4% | 4.6% | 2.7% | 12.4% | 2.5% | 3.6% | 2.3% | 13.8% | 1.4% | 8% | 8.8% | 1.5%
| Architectural | 20% | Side Walk External Works | Wall External Works | Roof External Works | Floor Interior Works | Wall Interior Works | Roof Interior Works
|  |  | 2.48% | 18.5% | 17.02% | 32.33% | 23.57% | 6.1%

## Equipment
Job Phases And Work Steps (Onshore Facilities) Equipment Packages Discipline
row | JOB PHASES | W.F | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8 | WORK STEP9 | WORK STEP10 | WORK STEP11 | WORK STEP12 | WORK STEP13
1 | Drum/Vessel |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 8% | 60% | 8% | 1% | 8% | 5%
2 | Boiler |  | Material Handling | Chipping & Padding | Installation | Align | Steel work, Coil Connection | Accessory Install | Final Inspection
|  |  | 10% | 8% | 40% | 10% | 15% | 12% | 5%
3 | Column |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 8% | 60% | 8% | 1% | 8% | 5%
4 | Reactor |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 8% | 60% | 8% | 1% | 8% | 5%
5 | Heat Exchanger |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 8% | 60% | 8% | 1% | 8% | 5%
6 | Filter |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | External Installation | Final Inspection
|  |  | 10% | 8% | 60% | 8% | 1% | 8% | 5%
7 | Furnace Blower/ Heater |  | Material Handling | Installation | Alignment / Leveling | Internal Accessories | Grouting | External Installation | Final Inspection
|  |  | 0% | 70% | 7% | 5% | 2.5% | 10% | 5%
8 | Ejector |  | Material Handling | Installation | Alignment / Leveling | Final Inspection
|  |  | 10% | 75% | 10% | 5%
9 | Gas Compressor/Turbine |  | Material Handling | Chipping & Padding | Turbine/Generator Install | 1st Alignment | Steel Structure/Platform | Duct/Accessory | 2nd Align/Grouting/Coupling | Grouting | Final Inspection
|  |  | 10% | 5% | 43% | 15% | 10% | 4% | 3% | 2% | 8%
10 | Compressor |  | Material Handling | Chipping & Padding | Installation | Alignment / Leveling | Grouting | Final Alignment / Piping | Final Inspection
|  |  | 10% | 8% | 52% | 10% | 4% | 8% | 8%
11 | Mixer Agitator |  | Material Handling | Installation | Final Inspection
|  |  | 10% | 85% | 5%
12 | Pump |  | Material Handling | Chipping & Padding | Installation | 1st Alignment | Grouting | 2nd Alignment | Final Inspection
|  |  | 10% | 8% | 52% | 15% | 5% | 5% | 5%
13 | Package Equipment |  | Material Handling | Chipping & Padding | Installation | Skid Alignment/Leveling | Grouting | Accessory Install | Final Inspection
|  |  | 10% | 8% | 60% | 10% | 5% | 2% | 5%
14 | Overhead Crane |  | Material Handling | Installing Rail Frame | Main Frame Fabrication | Crane Install | Load Test | Final Inspection
|  |  | 8% | 37% | 30% | 18% | 2% | 5%
15 | Internals/Tray |  | Material Handling | Install | Final Inspection
|  |  | 10% | 85% | 5%
16 | Air Cooler |  | Material Handling | Structure Ground Assembly | Structure Installation | Tube Bundle Erection | Ground Assembly of Plenum | Plenum Chamber Installation | Motor Installation | Blade Installation | Pulley Installation | Ladder & Platform | Pully Adjustment | Shaft Alignment/Leveling | Final Inspection
|  |  | 10% | 15% | 6% | 20% | 8% | 10% | 4% | 5% | 4% | 4% | 4% | 5% | 5%
17 | Field Fabricated Tank |  | Material Handling | Foundation Preparation | Installation & Welding of Bottom Plate | Installation & Welding of Annular Plate | Installation & Welding of Shell Plate | Installation & Welding of Roof Plate (Including Roof Support) | Installation & Welding of Accessory | Hydro Test and Drainage & Cleaning out | Final Inspection
|  |  | 0% | 5% | 12% | 3% | 45% | 15% | 8% | 7% | 5%
18 | Condensate Tank |  | Electrical Work (Cathodic Protection) | Installation & Welding of Bottom Plate | Installation & Welding of Annular Plate | Installation & Welding of Shell Plate | Installation & Welding of Roof Plate (Including Roof Support) | Installation & Welding of Accessory | Hydro Test and Drainage & Cleaning out | Final Inspection
|  |  | 2% | 6% | 3% | 53% | 17% | 6% | 8% | 5%
19 | LPG Tank |  | Wall Plate | Roof Assembly / Installation | Accessory Installation | Mechanical Work | Insulation | Air Test | Hydro Test and Drainage & Cleaning out | Final Inspection
|  |  | 37% | 10% | 6% | 25% | 11% | 2% | 4% | 5%
20 | Flare |  | Material Handling | Tip Assembling | Derrick Installation | Pipe Service Installation | Align | Platform/Stair | Final Inspection
|  |  | 10% | 4% | 50% | 20% | 6% | 5% | 5%

## Steel Work
Job Phases And Work Steps (Onshore Facilities) Steel Work Discipline
row | JOB PHASES | WF | WORK STEP1 | WORK STEP2 | WORK STEP3 | WORK STEP4 | WORK STEP5 | WORK STEP6 | WORK STEP7 | WORK STEP8
1 | Equipment Structure Erection |  | MATERIAL DELIVERY AT JOB SITE | Chipping & Padding | ERECTION | ALIGNMENT | BOLT TIGHTENING | GROUTING | PUNCH CLEAR
|  |  | 10% | 5% | 69% | 5% | 5% | 5% | 1%
2 | Pipe Rack Erection |  | MATERIAL DELIVERY AT JOB SITE | Chipping & Padding | ERECTION | ALIGNMENT | BOLT TIGHTENING | GROUTING | PUNCH CLEAR
|  |  | 15% | 5% | 64% | 5% | 5% | 5% | 1%
3 | Platform & Ladder |  | MATERIAL DELIVERY AT JOB SITE | ERECTION and INSTALLATION | BOLT TIGHTENING | PUNCH CLEAR
|  |  | 15% | 78% | 6% | 1%
4 | Shelter |  | MATERIAL DELIVERY AT JOB SITE | Chipping & Padding | ERECTION | ALIGNMENT | BOLT TIGHTENING | GROUTING | Cladding | PUNCH CLEAR
|  |  | 10% | 5% | 60% | 8% | 5% | 5% | 6% | 1%