## Sheet1
| Start Date | Duration
Planning Meeting | 2016-05-03 | 1
Develop Questionnaire | 2016-05-04 | 11
Print and Mail Questionnaire | 2016-05-18 | 9
Receive Responses | 2016-05-21 | 15
Data Entry | 2016-05-21 | 18
Data Analysis | 2016-06-08 | 4
Write Report | 2016-06-14 | 12
Distribute Draft Report | 2016-06-28 | 2
Solicit Comments | 2016-06-29 | 5
Finalize Report | 2016-07-05 | 6
Distribute to Board | 2016-07-12 | 2
Board Meeting | 2016-07-20 | 1