## Tasks
Name | Duration
Log footage | 5 days
Record rough narration | 4 days
Paper edit footage | 10 days
Rough cut edit | 8 days
Fine cut edit | 7 days
Hold formal approval showing | 1 day
Add dialog | 2 days
Record final narration | 5 days
Add head and tail titles | 5 days
Add final music | 3 days
Print internegative of film | 3 days
Clone dubbing masters of audio tape | 4 days
Archive master film and audio tape | 0.5 days
Hand off masters to distributor | 0 days